ROADMAP FOR DEVELOPMENT OF ANALYSIS NOTE OF TRADE IN GOOD

| N° | ACTIVITIES | TASKS | IMPLEMENTATION DATE& VENUE | PARTICIPANTS FUNDING REQUEST |
| --- | --- | --- | --- | --- |
| 1 | Development of Draft Analysis Note of ECOWAS External Trade Statistics( Trade in Goods) 2016 to 2025 | - Arnaud updates trade statistics to 2025 - Wumi compiles the analysis - Bring out challenges of 2025 trade statistics - Prescribe possible solutions to the challenges - Finalise the recruitment of Trade Statistics Consultant | ECOWAS Commission, 30 September, 2026 | - No budgetary implication |
| 2 | Regional workshop on Member States Capacity building in EUROTRACE SQL Server and finalisation of 2016-2025 national trade in goods data collection | - Review the template according to the data sharing protocol with the possibility of HS10 | Last week of September 2026 | Total participants: 45 - 2 per MS (INS and Custom Service) = 24 - Directorate Trade, Customs and Taxation, Agric, ARAA, DBT= 5 - DRS: PO=2 - DRS= 1 - Resource person= 4 - Interpreters = 4 |
|  |  | - Send the revised template to all MS | 28 to 30 of September 2026 |  |
|  |  | - Use the existing ToR with WB Concept Note to draft memo to seek commissioner approval | Last week of September 2026 |  |
|  |  | - After Approval, send Invitation letters to MS | First week of October |  |
|  |  | - Organize the workshop with UNSD on IMTS 2026 in Lagos to collate national trade statistics and development of Regional MDMX protocol | 19 to 24 of October 2026 |  |
| 3 | TWG meeting to analyse national data and compile regional 2016 to 2025 statistics of Trade in goods | ToR, Memo & Invitation Letters TWG in Zuma, Niger State (Need SQL server licence) | 2 to 7 November 2026 | Total participants: 15 max - DRS staff : PO=2 - Resource person= 3 - Trade & Customs and Taxation Directorate=2 |
| 4 | Development and finalisation of Analysis Note 2016-2025 in 3 official Languages and Alignment, Layout and printing of the Analysis Mote | ToR, Memo & Invitation Letters TWG in Abuja (Zuma Rock) | 16 to 21st of November 2026 | Total participants: 12 - DRS: PO=2 - Resource persons= 6 - Directorate Trade, Custom, Agric, Finance= 4 |
| 5 | Regional Validation workshop | ToR, Memo & Invitation Letters Venue to be determined | 30 November to 4 December 2026 | Total participants: 30 - 12 MS (INS) - Directorate Trade, Custom, Agric, ARAA, Finance= 5 - DRS: PO=2 - DRS= 1 - Consultants= 2 - Resource persons= 1 - Interpreters = 4 |